## Hybrid Project Plan
| PROJECT NAME | STUDENT/TEAM | START DATE | END DATE |  | OVERALL PROGRESS |  |  | PROJECT DELIVERABLE
| Project Plant | Purithat Lamlertkertkan | 2024-04-08 | 2023-07-17 |  | 0% |  |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | HOURS | STATUS | COMMENTS
| Project Plan | Research | Your name | 50% | 2024-04-08 | 2024-07-17 | 101 | 0 | Not Started
| Set up |  |  | 0% |  |  |  |  | Not Started
| DeployScene |  |  | 0% |  |  |  |  | Not Started
| Farm Scene |  |  | 0% |  |  |  |  | Not Started
| Character Control |  |  | 0% |  |  |  |  | Not Started
| Enemy behavior |  |  | 0% |  |  |  |  | Not Started
|  |  |  | 0% |  |  |  |  | Not Started
|  |  |  | 50% |  |  |  |  | Not Started
| Sprint 1 : <sprint focus> | Milestone |  | 0% | 2024-04-22 | 2024-04-29 | 0 | 5 | Not Started
| Deploy Scene setup | Project Setup | [5 empty] | 1 | Complete | The scene created
| Character behavior | Programming | [5 empty] | 2 | Complete | Moving, Shooting
| Reserching | Documentation | [5 empty] | 2 | Complete | the Character behavior reserch
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 2: <sprint focus> | Milestone |  | 0% | 2024-04-29 | 2024-05-06 | 0 | 4 | Not Started | Remove the tfarming feature due to the time consuming to polishing of the system
| Enemy behavior | Programming | [5 empty] | 1 | Complete
|  | "" | [6 empty] | Not Started
| Reserching | Documentation | [5 empty] | 3 | Complete
| Farming System | Programming | [6 empty] | Cancelled
| Farming scene setup | Project Setup | [6 empty] | Cancelled
| Sprint 3: <sprint focus> | Milestone |  | 0% | 2024-05-06 | 2024-05-13 | 0 | 8 | Not Started | The coding on the system is Complete
| Hub world setup | "" | [5 empty] | 2 | Complete
| Store system | Programming | [5 empty] | 2 | Complete
| Reserching | Documentation | [5 empty] | 4 | Complete
| Hub World System | Programming | [6 empty] | Complete
|  | "" | [6 empty] | Not Started
| Sprint 4: <sprint focus> | Milestone |  | 0% | 2024-05-13 | 2024-05-20 | 0 | 4 | Not Started
| Art(Map , Items) | Art | [5 empty] | 4 | In Progress
Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 5: <sprint focus> | Milestone |  | 0% | 2024-05-20 | 2024-05-27 | 0 | 4 | Not Started
| Art(Gun, player character, Enemy) | Art | [5 empty] | 1 | Not Started
| Animation | Animation | [5 empty] | 3 | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 6: <sprint focus> | Milestone |  | 0% | 2024-05-27 | 2024-06-03 | 0 | 6 | Not Started
| Animation setup | Animation | [5 empty] | 2 | Not Started
| Sound | Sound | [5 empty] | 2 | Not Started
| Reserching | Documentation | [5 empty] | 2 | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Sprint 7: <sprint focus> | Milestone |  | 50% | 2024-06-03 | 2024-06-10 | 0 | 4 | Not Started
| Clean up | Configuration | [5 empty] | 3 | Not Started
| Connect all scene | Configuration | [5 empty] | 1 | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
|  | "" | [6 empty] | Not Started
| Final Project | Polishing and Preparing Presentation |  | 25% | 2024-06-10 | 2024-06-17 |  |  | Not Started
| Final Delivery | Final |  | 25% | 2024-04-22 | 2024-06-17 |  |  | Not Started
Note on A5: Mark with X to Discuss about the risks

## Data
FEATURE TYPE
Art
Programming
Documentation
Research
Animation
Sound
Project Setup
Configuration
""
Final